## Sheet1
FarmLInk-Web Gantt Chart
[5 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10
 | time axis 2025-07-01 to 2025-09-06
Task Name | Assigned | Start Date → End Date | Work Days | Progress | mon | tue | wed | thu | fri | mon | tue | wed | thu | fri | mon | tue | wed | thu | fri | mon | tue | wed | thu | fri | mon | tue | wed | thu | fri | mon | tue | wed | thu | fri | mon | tue | wed | thu | fri | mon | tue | wed | thu | fri | mon | tue | wed | thu | fri | mon | tue | wed | thu | fri
A: Requirement Gathering | Mahmodul , Nabila | July 1 → July 11 | 9
A1: Stakeholder interviews & surveys |  | July 1 → July 5 | 5 | bar: 2025-07-01 to 2025-07-05
A2: Identify system goals & scope |  | July 3 → July 4 | 2 | bar: 2025-07-03 to 2025-07-04
A3: Gather functional requirements |  | July 8 → July 8 | 1 | bar: 2025-07-08
A4: Gather non-functional requirements |  | July 9 → July 9 | 1 | bar: 2025-07-09
A5: Create requirement specification document |  | July 10 → July 10 | 1 | bar: 2025-07-10
A6: Review & finalize requirements with team |  | July 11 → July 11 | 1 | bar: 2025-07-11
B: UI/UX Design | Mubin | July 8 → July 19 | 10
B1: Research & gather design inspirations |  | July 8 → July 12 | 5 | bar: 2025-07-08 to 2025-07-12
B2: Create low-fidelity wireframes |  | July 9 → July 10 | 2 | bar: 2025-07-09 to 2025-07-10
B3: High-fidelity UI mockups (homepage, login, dashboard) |  | July 11 → July 15 | 3 | bar: 2025-07-11 to 2025-07-15
B4: User experience flow design |  | July 15 → July 16 | 2 | bar: 2025-07-15 to 2025-07-16
B5: Create interactive prototype |  | July 16 → July 18 | 3 | bar: 2025-07-16 to 2025-07-18
B6: Review & feedback from team |  | July 19 → July 19 | 1 | bar: 2025-07-19
C: Database Design | Mahmodul | July 15 → July 26 | 10
C1: Identify entities & relationships |  | July 15 → July 17 | 3 | bar: 2025-07-15 to 2025-07-18
C2: Draw ER diagram |  | July 18 → July 18 | 1 | bar: 2025-07-18
C3: Normalize database schema |  | July 18 → July 18 | 1 | bar: 2025-07-18
C4: Define tables, attributes & constraints |  | July 19 → July 24 | 4 | bar: 2025-07-19 to 2025-07-24
C5: Setup database in SQL (or chosen DB) |  | July 25 → July 25 | 1 | bar: 2025-07-25
C6: Review and refine schema |  | July 25 → July 26 | 2 | bar: 2025-07-25 to 2025-07-26
D: Authentication & Role-Based Access | Mubin | July 22 →July 23 | 2
D1: Setup user authentication system |  | July 22 →July 22 | 1 | bar: 2025-07-22
D2: Implement role-based access control |  | July 22 →July 22 | 1 | bar: 2025-07-22
D3: Secure password hashing & validation |  | July 22 →July 22 | 1 | bar: 2025-07-22
D4: Role-specific dashboard redirection after login |  | July 22 →July 23 | 1 | bar: 2025-07-23
D5: Middleware for authorization checks in APIs |  | July 22 →July 23 | 1 | bar: 2025-07-23
D6: Testing login & access restrictions |  | July 22 →July 23 | 1 | bar: 2025-07-23
E: Backend Development – Farmer Module | Diganta | July 17 → Aug 5 | 14
E1: Product listing & management |  | July 17 → july 22 | 4 | bar: 2025-07-17 to 2025-07-22
E2: Order management for farmers |  | July 23 → July 29 | 5 | bar: 2025-07-23 to 2025-07-29
E3: Farmer dashboard API |  | July 29 → Aug 1 | 3 | bar: 2025-07-29 to 2025-08-01
E4: Unit testing & debugging |  | Aug 2 → Aug 5 | 2 | bar: 2025-08-02 to 2025-08-05
F: Backend Development – Buyer Module | Mubin | July 24 → Aug 6 | 10
F1: Product browsing & searching |  | July 24 → July 25 | 2 | bar: 2025-07-24 to 2025-07-25
F2: Shopping cart / bucket system |  | July 25 → July 25 | 1 | bar: 2025-07-25
F3: Order placement & payment integration |  | July 26 → July 30 | 3 | bar: 2025-07-26 to 2025-07-30
F4: Buyer dashboard API |  | July 31 → Aug 2 | 3 | bar: 2025-07-31 to 2025-08-02
F5: Unit testing & debugging |  | Aug 5 → Aug 6 | 2 | bar: 2025-08-05 to 2025-08-06
G: Backend Development – Agent Module | Diganta | Aug 7 → Aug 22 | 13
G1: Commission handling & transaction tracking |  | Aug 16 → Aug 19 | 2 | bar: 2025-08-16 to 2025-08-19
G2: Bulk request handling |  | Aug 13 → Aug 15 | 3 | bar: 2025-08-13 to 2025-08-15
G3: Agent product management |  | Aug 7 → Aug 12 | 4 | bar: 2025-08-07 to 2025-08-12
G4: Agent dashboard API |  | Aug 20 → Aug 21 | 2 | bar: 2025-08-20 to 2025-08-21
G5: Unit testing & debugging |  | Aug 22 → Aug 22 | 1 | bar: 2025-08-21
H: Backend Development – Admin Module | Mubin | Aug 7 → Aug 21 | 11
H1: User management (farmers, buyers, agents) |  | Aug 7 → Aug 9 | 3 | bar: 2025-08-07 to 2025-08-09
H2: Product approval & monitoring |  | Aug 12 → Aug 13 | 2 | bar: 2025-08-12 to 2025-08-13
H3: Order & transaction tracking |  | Aug 14 → Aug 16 | 3 | bar: 2025-08-14 to 2025-08-16
H4: Admin dashboard API |  | Aug 19 → Aug 20 | 2 | bar: 2025-08-19 to 2025-08-20
H5: Unit testing & debugging |  | Aug 21 → Aug 21 | 1 | bar: 2025-08-21
I: Frontend Development | Mahmodul | July 29 → Aug 30 | 25
H1: Setup frontend framework (React/Angular/etc.) |  | July 29 → July 30 | 2 | bar: 2025-07-29 to 2025-07-30
H2: Implement navigation & routing |  | July 31 → Aug 1 | 2 | bar: 2025-07-31 to 2025-08-01
H3: Develop farmer module UI |  | Aug 2 → Aug 9 | 6 | bar: 2025-08-02 to 2025-08-09
H4: Develop buyer module UI |  | Aug 12 → Aug 16 | 5 | bar: 2025-08-12 to 2025-08-16
H5: Develop agent module UI |  | Aug 19 → Aug 22 | 4 | bar: 2025-08-19 to 2025-08-22
H6: Develop admin module UI |  | Aug 23 → Aug 30 | 6 | bar: 2025-08-23 to 2025-08-30
J: Integration & Testing | Nabila | Aug 5 → Aug 30 | 20
I1: Backend API integration with frontend |  | Aug 5 → Aug 6 | 2 | bar: 2025-08-05 to 2025-08-06
I2: Database connection & validation |  | Aug 7 → Aug 8 | 2 | bar: 2025-08-07 to 2025-08-08
I3: Module-wise testing (Farmer, Buyer, Agent, Admin) |  | Aug 9 → Aug 15 | 5 | bar: 2025-08-09 to 2025-08-15
I4: End-to-end functional testing |  | Aug 16 → Aug 20 | 3 | bar: 2025-08-16 to 2025-08-20
I5: Bug fixing & improvements |  | Aug 21 → Aug 27 | 5 | bar: 2025-08-21 to 2025-08-27
I6: Final integration review |  | Aug 28 → Aug 30 | 3 | bar: 2025-08-28 to 2025-08-30
K: Deployment & System Testing | Mubin , Diganta | Aug 23 → Sep 3 | 8
J1: Setup deployment environment (server/cloud) |  | Aug 23 → Aug 23 | 1 | bar: 2025-08-23
J2: Database migration & deployment setup |  | Aug 26 → Aug 26 | 1 | bar: 2025-08-26
J3: Deploy backend services |  | Aug 27 → Aug 27 | 1 | bar: 2025-08-27
J4: Deploy frontend application |  | Aug 28 → Aug 28 | 1 | bar: 2025-08-28
J5: Security & performance testing |  | Aug 29 → Aug 29 | 1 | bar: 2025-08-29
J6: Final bug fixing & patch updates |  | Aug 30 → Aug 30 | 1 | bar: 2025-08-30
J7: Handover & documentation |  | Sep 2 → Sep 3 | 2 | bar: 2025-09-02 to 2025-09-03